## Estimated Guide
Use case | Module | Country | Phase | Task | Sub Task | Owner | Estimated duration | Baseline 27-05-2020 | Sprint20200520 (*number indictates sprint start date ) | Sprint20200603 | Sprint20200617 | Sprint20200701 | Sprint20200715 | Sprint20200729 | Sprint20200812 | Sprint20200826 | Sprint20200909 | Sprint20200923 | Sprint20201007 | Sprint20201021 | Sprint20201104 | Sprint20201118 | Sprint20201202 |  | 2021
ETM | General |  | Concept and preparation | Idea assessment |  | use case lead |  | Completed
|  |  |  | Product brief |  | use case lead |  | Completed
|  |  |  | Scope of work |  | use case lead |  |  | Planned | Planned
ETM | General |  | Design | HLD | atesio model | use case lead |  |  | Planned | Planned | Delayed | Delayed | Delayed
[5 empty] | UI and Visualisation | use case lead |  |  | Planned | Planned | Concluded with delay
ETM | General |  | Design | Off line POC |  | use case lead |  | Completed
ETM | General |  | Design | TDS | UPM | Jared |  | Completed
[5 empty] | OSM | Jared |  | Completed
[5 empty] | Copernicus | Jared |  | Completed
[5 empty] | Population density | Jared |  | Completed
[5 empty] | Cell radio electric | Jared |  |  | Planned | Concluded
[5 empty] | Atoll Pathloss | Jared |  |  | Planned | Concluded
ETM | Market Implementation Phase 1 | IT | Design | Data sharing approval | UPM | Jared |  | Completed
[5 empty] | OSM | Jared |  | Completed
[5 empty] | Copernicus | Jared |  | Completed
[5 empty] | Population density | Jared |  | Completed
[5 empty] | Cell radio electric | Jared |  |  |  |  | Planned | Concluded with delay
[5 empty] | Atoll Pathloss | Jared |  |  |  |  | Planned | Concluded with delay
ETM | Market Implementation Phase 1 | IT | Design | Use case Approval |  | Jared |  | Completed
ETM | General |  | Design | Vendor enablement | VPN | use case lead |  |  | Completed
[5 empty] | vodafone.com identitiy | use case lead |  |  | Planned | Completed
[5 empty] | GCP access | use case lead |  |  |  | Planned | Delayed | Delayed
ETM | Market Implementation Phase 1 | IT | Design | Data ingestion | UPM | Greg |  | Completed
[5 empty] | OSM | Greg |  | Completed
[5 empty] | Copernicus | Greg |  | Completed
[5 empty] | Population density | Greg |  | Completed
[5 empty] | Cell radio electric | Greg | [5 empty] | Planned | Delayed
[5 empty] | Atoll Pathloss/Antenna cat | Greg | [5 empty] | Planned | [5 empty] | Delayed
ETM | Market Implementation Phase 1 | IT | Design | Vendor environment | GCP architecture conclusion | Greg |  |  | Completed |  |  | Revised
[5 empty] | Kubernetes architecture | atesio/Greg | [11 empty] | planned
[5 empty] | standard GCP compute environment | Greg |  |  |  |  | Planned | Concluded with delay
[5 empty] | Kubernetes compute environment | Greg | [11 empty] | tbc by Neuron
[5 empty] | Web UI environment approval | Greg |  |  |  |  | tbc by Neuron
ETM | Market Implementation Phase 1 | IT | Design | LLD1.0 | atesio model | use case lead |  |  |  |  | Planned | Delayed | [5 empty] | Delayed
ETM | General deployment | IT |  |  | UI and Visualisation | use case lead |  |  |  |  | Planned | Delayed | [5 empty] | Delayed
ETM | Market Implementation Phase 1 | IT | Implementation | Coding atesio model | General implementation on GCP | atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Initialization VF-IT | atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Additional UPM KPIs | atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Best-sector approach for cell service areas | atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Distribution of demand across cells with a sector | atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Unit testing | atesio | [12 empty] | Planned
ETM | Market Implementation Phase 1 | IT | Implementation | Coding UI | User interface | Vodafone/atesio | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Unit testing | Vodafone | [12 empty] | Planned
ETM | Market Implementation Phase 1 | IT | Implementation | Coding visualisation | Viusaulisation prototype | Vodafone | [5 empty] | Planned | [5 empty] | Planned | Planned
[5 empty] | Testing | Vodafone | [12 empty] | Planned
ETM | Market Implementation Phase 1 | IT |  | Documentation | Technical documentation/wiki | atesio | [5 empty] | Planned
ETM | Market Implementation Phase 1 | IT | Testing | Vendor Test (isolated) environment testing | Security UI Pen-Testing | Vodafone | [13 empty] | Planned | Planned
[5 empty] | UI Security & visualisation issues resolution | Vodafone | [13 empty] | Planned | Planned
|  |  |  | Non live market | Integration testing | atesio/Vodafone | [13 empty] | Planned | Planned
[5 empty] | Performance testing | atesio | [13 empty] | Planned | Planned
[5 empty] | Model performance & integration optimisation | Vodafone/atesio | [13 empty] | Planned | Planned
[5 empty] | Deployment | Vodafone/atesio | [14 empty] | Planned
|  |  |  | LLDV2.0 |  | atesio/Vodafone | [14 empty] | Planned | Planned
|  |  |  | Deployment specification |  | atesio/Vodafone | [15 empty] | Planned
|  |  |  | UAT |  | Vodafone | [15 empty] | Planned
ETM | Market Implementation Phase 1 | IT | Deployment | Deployment |  | Greg | [15 empty] | Planned
|  |  |  | Testing |  | Greg | [15 empty] | Planned
|  |  |  | Customer acceptance |  | Vodafone IT | [15 empty] | Planned
ETM |  |  | Implementation | SSO integration |  | Vodafone | [16 empty] | Planned | Planned

## Sheet1
Andreas: 27.7.-9.8.
Benjamin: 13.-24.7.
Dario: 27.7.-9.8.
Uli: 25.6.-3.7.
Andrea: 29-6 - 15-7
Frank: 21.7- 12.8
Mohamed: 24.9-4.10
Ahmed: non
Abdalah: 27.7-30.7, 31.8-4.9
VF-IT: 10.8- 18.8